## Blad1
Category | Sub-Category | Item Naam | Code | Prioriteit | Maker | DickPoints | Begin Datum | Eind Datum | Done
Concept Art
| Levels |  | 1CA_LE
|  | GrasLevel | CA_LE_GL
| Character |  | 1CA_CH
|  | Nina | CA_CH_NN
| Props |  | 1CA_PR
|  | Wooden Sword | 1CA_PR_WS
2D Art
| Textures |  | 2D_TX
|  | Grond | 2D_TX_G | 1 | Ruben | 1
|  | Gras Muur | 2D_TX_GM | 1 | Ruben | 2
|  | BoomStronk | 2D_TX_BS | 1 | Ruben | 4
|  | Zand | 2D_TX_Z | 1 | Ruben | 1
|  | Zandbak | 2D_TX_ZA | 1 | Ruben | 1
|  | Waterplas | 2D_TX_WP | 1 | Ruben | 2
|  | Poppenhuis | 2D_TX_PH | 2 | Kilian | 3
|  | Schuur | 2D_TX_SC | 1 | Ruben | 3
|  | Spinnenweb | 2D_TX_SW | 3 | Jesse | 2
|  | Gras Sprietjes | 2D_TX_SP | 3 | Ruben | 2
|  | Stenen | 2D_TX_S | 3 | Kilian | 1
|  | Suikerklontje | 2D_TX_SK | 2 | Kilian | 1
|  | PlatenStaak | 2D_TX_PS | 1 | Jesse | 3
|  | Madeliefjes | 2D_TX_ML | 2 | Jesse | 2
|  | Naald | 2D_TX_N | 1 | Jesse | 3
|  | Springveer | 2D_TX_SPR | 1 | Ruben | 1
|  | Houten zwaard | 2D_TX_HZ | 1 | Kilian | 2
|  | Knoopschild | 2D_TX_KS | 1 | Kilian | 2
|  | Houten Platform | 2D_TX_HZ | 3 | Ruben | 1
|  | Mier 1 | 2D_TX_M1 |  | Kilian | 4
|  | Mier 2 | 2D_TX_M2 |  | Kilian | 1
|  | Mier 3 | 2D_TX_M3 |  | Kilian | 1
|  | Nina | 2D_TX_NN | 1 | Jesse | 5
|  | Schepje | 2D_TX_SC | 2 | Kilian | 1
|  | Hark | 2D_TX_H | 2 | Kilian | 1
|  | Sandvormpje | 2D_TX_SV | 3 | Kilian | 1
|  | Blaadjes | 2D_TX_BL | 2 | Ruben | 2
|  | Stoeltje | 2D_TX_ST | 3 | Jesse | 2
|  | Kapstok | 2D_TX_KA | 3 | Jesse | 1
|  | Trap | 2D_TX_T | 3 | Ruben | 2
|  | Libelle | 2D_TX_LB | 2 | Kilian | 4
|  | Mini Ray | 2D_TX_MR | 1 | Ruben | 4
|  | Tafel | 2D_TX_T | 1 | Kilian | 2
|  | TL Buis | 2D_TX_TB | 3 | Jesse | 1
|  | Lightstaber | 2D_TX_LS | 3 | Jesse | 3
|  | Gif Fles | 2D_TX_GF | 2 | Kilian | 2
|  | Flessendop | 2D_TX_FD | 2 | Kilian | 2
|  | Daddylegs | 2D_TX_DL | 1 | Kilian | 3
|  | Emmer | 2D_TX_E | 3 | Kilian | 1
| HUD |  | 2D_HUD
|  | Full Heart |  | 1 | Jesse | 1
|  | Half Heart |  | 1 | Jesse | 1
|  | Stamina Bar |  | 3 | Jesse | 1
|  | Denk Wolkje |  | 3 | Jesse | 1
|  | Adem Bar |  | 3 | jesse | 1
|  | Menu |  | 1 | Kilian | 3
|  | Game Over |  | 1 | Ruben | 2
|  | Intro Comic |  | 1 | ?
|  | Madeliefjes Schild |  | 3 | Jesse | 2
| Sprites |  | 2D_SP
3D Art
| Environment |  | 3D_E
|  | Grond | 3D_E_G | 1 | Ruben | 2 | 2015-09-14 | 2015-09-18
|  | Grasmuur | 3D_E_GM | 1 | Ruben | 1 | 2015-09-14 | 2015-09-18
|  | Zand | 3D_E_Z | 1 | Ruben | 2 | 2015-09-14 | 2015-09-18
|  | Zandbak | 3D_E_ZA | 1 | Ruben | 2
|  | Waterplas | 3D_E_WP | 1 | Ruben | 1
|  | Schuur | 3D_E_SC | 1 | Ruben | 3
|  | Skybox | 3D_E_SK | 3 | Ruben | 1
| Main Character |  | 3D_MC
|  | Nina | 3D_MC_NN | 1 | Jesse | 5 | 2015-09-14 | 2015-09-18
| Npc's |  | 3D_NP
|  | Libelle | 3D_NP_LB | 2 | Kilian | 3
| Buildings |  | 3D_B
|  | Boomstronk | 3D_B_BS | 1 | Ruben | 5 | 2015-09-21 | 2015-09-25
|  | Poppenhuis | 3D_B_PH | 2 | Kilian | 4
| Props |  | 3D_P
|  | Spinnenweb | 3D_P_SW | 3 | Jesse | 2
|  | Gras Sprietjes | 3D_P_GS | 3 | Ruben | 1
|  | Stenen | 3D_P_S | 3 | Kilian | 1
|  | Suikerklontje | 3D_P_SK | 2 | Kilian | 1
|  | PlantenStaak | 3D_P_PS | 1 | Jesse | 3
|  | Madeliefjes | 3D_P_ML | 2 | Jesse | 2
|  | Naald | 3D_P_N | 1 | Jesse | 2
|  | Springveer | 3D_P_SPR | 1 | Ruben | 1
|  | Houten Zwaard | 3D_P_HZ | 1 | Kilian | 2 | 2015-09-21 | 2015-09-25
|  | Knoopschild | 3D_P_KS | 1 | Kilian | 2 | 2015-09-21 | 2015-09-25
|  | Houten Platform | 3D_P_HP | 3 | Ruben | 1
|  | Schepje | 3D_P_SC | 2 | Kilian | 2
|  | Hark | 3D_P_H | 2 | Kilian | 2
|  | Sandvormpje | 3D_P_SV | 3 | Kilian | 1
|  | Blaadjes | 3D_P_B | 2 | Ruben | 1
|  | Stoeltje | 3D_P_ST | 3 | Jesse | 2
|  | Kapstok | 3D_P_KA | 3 | Jesse | 1
|  | Trap | 3D_P_T | 3 | Ruben | 1
|  | Miniray | 3D_P_MR | 1 | Ruben | 4
|  | Tafel | 3D_P_TA | 1 | Kilian | 1
|  | TL buis | 3D_P_TB | 3 | Jesse | 1
|  | Lightsaber | 3D_P_LS | 3 | Jesse | 3
|  | Gif fles | 3D_P_GF | 2 | Kilian | 2
|  | Flessendop | 3D_P_FD | 2 | Kilian | 2
|  | DaddyLegs | 3D_P_DL | 1 | Kilian | 3 | 2015-09-21 | 2015-09-25
|  | Emmer | 3D_P_E | 3 | Kilian | 2
| Enemy's |  | 3D_E
|  | Mier | 3D_E_M | 1 | Kilian | 5 | 2015-09-14 | 2015-09-18
Unwraps
| Main Character |  | 4UW_MC
|  | Nina | 4UW_MC_NN | 1 | Jesse | 5
| Npc's |  | 4UW_NP
|  | Libelle | 4UW_NP_LB | 2 | Kilean | 5
| Environment |  | 4UW_WT
|  | Grond | 4UW_E_G | 1 | Ruben | 1
|  | Grasmuur | 4UW_E_GM | 1 | Ruben | 1
|  | Zand | 4UW_E_ZA | 1 | Ruben | 1
|  | Zandbak | 4UW_E_ZB | 1 | Ruben | 1
|  | Waterplas | 4UW_E_W | 1 | Ruben | 1
|  | Schuur | 4UW_E_S | 1 | Ruben | 3
|  | Skybox | 4UW_E_SK | 3 | Ruben | 1
| Buildings |  | 4UW_B
|  | Boomstronk | 4UW_B_BS | 1 | Ruben | 4
|  | Poppenhuis | 4UW_B_PH | 2 | Kilian | 4
| Props |  | 4UW_P
|  | Spinnenweb | 4UW_P_SW | 3 | Jesse | 1
|  | Gras Sprietjes | 4UW_P_GP | 3 | Ruben | 1
|  | Stenen | 4UW_P_S | 3 | Kilian | 2
|  | Suikerklontje | 4UW_P_SK | 2 | Kilian | 1
|  | Plantenstaak | 4UW_P_PS | 1 | Jesse | 2
|  | Madeliefjes | 4UW_P_ML | 2 | Jesse | 2
|  | Naald | 4UW_P_N | 1 | Jesse | 2
|  | Springveer | 4UW_P_SPR | 1 | Ruben | 1
|  | Houten Zwaard | 4UW_P_HZ | 1 | Kilian | 2
|  | Knoopschild | 4UW_P_KS | 1 | Kilian | 3
|  | Houten Platform | 4UW_P_HP | 3 | Ruben | 1
|  | Schepje | 4UW_P_SC | 2 | Kilian | 3
|  | Hark | 4UW_P_H | 2 | Kilian | 3
|  | Sandvormpje | 4UW_P_SV | 3 | Kilian | 2
|  | Blaadjes | 4UW_P_B | 2 | Ruben | 1
|  | Stoeltje | 4UW_P_ST | 3 | Jesse | 1
|  | Kapstok | 4UW_P_K | 3 | Jesse | 1
|  | Trap | 4UW_P_T | 3 | Ruben | 1
|  | Miniray | 4UW_P_MR | 1 | Ruben | 5
|  | Tafel | 4UW_P_TA | 3 | Kilian | 2
|  | TL buis | 4UW_P_LA | 2 | Jesse | 1
|  | Lightsaber | 4UW_P_LI | 3 | Jesse | 3
|  | Gif fles | 4UW_P_GI | 2 | Kilian | 2
|  | Flessendop | 4UW_P_FL | 2 | Kilian | 2
|  | DaddyLegs | 4UW_P_DL | 1 | Ruben | 3
|  | Emmer | 4UW_P_E | 3 | Kilian | 2
| Enemy's |  | 4UW_E
|  | Mier | 4UW_E_M | 1 | Kilian | 5
Rigging
| Main Character |  | 5R_MC
|  | Nina | 5r_MC_NN | 1 | Jesse | 5
| Npc's |  | 5R_NP
|  | Libelle | 5R_NP_LB | 3 | Kilian | 4
| Enemy's |  | 5R_EN
|  | Mier | 5R_EN_M | 1 | Kilian | 5
Animaties
| Main Character |  | A6_MC
|  | Nina | A6_MC_NN | 1 | Jesse | 5
| Npc's |  | A6_NP
|  | Libelle | A6_NP_LB | 3 | Kilian | 2
|  | SpinnenWeb | A6_NP_SW | 3 | Jesse | 1
| Enemy's |  | A6_EN
|  | Mier | A6_EN_M | 2 | Ruben | 5
Sound
| Main Character |  | 7S_MC
Nina Lopen
Nina Rennen
Nina Schild
Nina springer
Nina adem Inhouden
Nina Gehit
Nina aanvallen
| Props |  | 7S_NP
Suikerkklonktje
Collectlebles
Spinnenweb
Blaadjes op water
Mina Ray Sounds
| Enemy's |  | 7S_EN
Mier Lopen
Mier aanvallen
Mier gehit
Mier Sounds
Libelle Sounds
| Level Design |  | 7S_LD
Background Music
Water
Gif
Scripts
| Adventure Gameplay |  | 8SC_AG
|  | Character Controller | 8SC_AG_CC | 1 | Harold
|  | Camara Controller | 8SC_AG_CCO | 1 | Alieke
|  | Health Player | 8SC_AG_HP | 1 | Alieke
|  | Fall Damage | 8SC_AG_FD | 2 | Mack
|  | Poison Death | 8SC_AG_PD | 3 | Mack
|  | Collecteble | 8SC_AG_CB | 3 | Alieke
|  | Interacting | 8SC_AG_I | 2 | Alieke
|  | Spawn/Checkpoint | 8SC_AG_SC | 2 | Mack
|  | Loading Screen | 8SC_AG_LS | 2 | Alieke
|  | Adam Inhouden | 8SC_AG_ADI | 3 | Harold
| H&S Gameplay |  | 8CS_HS
|  | Stamina | 8CS_HS_S | 2 | Mack
|  | Attack Player | 8CS_HS_AP | 1 | Alieke
|  | Attack Enemy | 8CS_HS_AE | 1 | Mack
|  | A.I Enemy | 8CS_HS_AIE | 2 | Harold
|  | Health Enemy | 8CS_HS_HE | 1 | Harold
|  | Defense Player | 8CS_HS_DP | 2 | Mack
|  | Enemy Spawner | 8CS_H_ES | 1 | Mack
| Puzzle Gameplay |  | 8CS_PG
|  | Spinnenweb | 8CS_PG_SW | 1 | Harold
|  | Water death | 8CS_PG_WD | 2 | Harold
|  | leaf moving | 8CS_PG_LS | 1 | Alieke
|  | Trigger Animation | 8CS_PG_TA | 3 | Alieke
| HUD |  | 8CS_HUD
|  | Health Bar | 8CS_HUD_HB | 1 | Harold
|  | Stamina Bar | 8CS_HUD_SB | 2 | Mack
|  | Madeliefjes Count | 8CS_HUD_MC | 3 | Alieke
|  | Denk Wolkje | 8CS_HUD_DW | 3 | Mack
|  | Menu Main | 8CS_HUD_MM | 1 | Mack
|  | Game Over | 8CS_HUD_GO | 2 | Alieke
|  | Game Pause | 8CS_HUD_GP | 2 | Alieke
|  | Comic Intro | 8CS_HUD_CI | 2 | Harold
|  | Comic Outro | 8CS_HUD_CO | 3 | Harold
Particals
| Npc's |  | 9P_WT
Nina Jump
Nina Lopen
| Props |  | 9P_P
Pick Up
Shield Hit
| Enemy's |  | 9P_EN
Mieren Hit
Gif Fles
Water
Mier Lopen
| Level Design |  | 9P_LD
[5 empty] | 3D Art | 80 | 14 Per week | niet per persoon